## MSB 001
HEXATECH |  |  | OPERATIONS CONTROL SERVICES |  |  |  |  | Issue No.: 1 | Document Effective Date: 01 Mar 2017 | Page 1 of 1
|  |  | Risk Assessment Form |  |  |  |  | Revision No.: 0 |  | Document Ref.: OCS-REC-R001
DEPARTMENT: |  | Project Department | [5 empty] | DATE: | '01 Mar 2017
FUNCTION/SCOPE: |  | To supply and install Distribution Board | [5 empty] | PROCEDURE NO.: | PD-PRO-03
Work Sequence | Work to be accomplished |  |  |  | Potential Hazard / Risk | Risk Rating | Long Term Precaution | Action By | Target Completion Date | Actual Completion Date
1 | To check and compare DB specification with shop drawing. |  |  |  | No risk. | None | Consult project manager if specification not met. | PE / PS
2 | To identify installation location. |  |  |  | No risk. | None | Consult project manager if unable to locate correct place to install DB. | PE / PS
3 | To apply work permit (if required). |  |  |  | No risk. | None | Consult project manager if unable to work permit rejected. | PE / PS
4 | Display warning sign board and work permit, barricade around the work area with hazard line. |  |  |  | Fall down / hit by falling object. | Low | Take necessary work safety precautions where necessary (ensure safety equipment are adequately provided). | PS | 31 Dec 2017
5 | Install the power Distribution Board. |  |  |  | Trip or fall. | Moderate | Barricade work area with hazard line. | PS
6 | Lay and install cable tray, conduit, trunking and cable. |  |  |  | Trip or fall. | Moderate | Barricade work area with hazard line. Check condition of ladder or scaffolding. | PS
7 | Connect the incoming cable to Distribution Board. |  |  |  | Electrocution. | Significant | Barricade work area with hazard line. Ensure no power supply on cables. | PS
8 | Connect the incoming cables from breaker or T.O.U. (tap off unit) to Distribution Board. |  |  |  | Electrocution. | Significant | Re-confirmation of termination point. Check phase termination. | PS
9 | Check the power supply for correct voltage (three phase and single phase). |  |  |  | Electrocution. | Moderate | Carry out testing with calibrated electrical measurement tools (ensure measuring tools are calibrated). | Wireman | 31 Dec 2017
10 | Record electrical testing and raise a testing report. Conduct commissioning of Distribution Board. |  |  |  | Electrocution. | Low | Request joint inspection with other customer representative to witness testing and commissioning. | Wireman
11 | Work area house keeping. |  |  |  | Fall down or hit by falling object. | Low | Wear PPE, follow clean as you work rule and make available cleaning tools (ensure cleaning tools are adequately provided). | PS | 31 Dec 2017
Prepared by: |  |  |  | Verified by: |  |  | Approved by: | Recorded by:
Signature: |  |  |  | Signature: |  |  | Signature: | Signature:
Name: |  |  |  | Name: |  |  | Name: | Name:
Appointment: |  |  |  | Appointment: IM |  |  | Appointment: MD | Appointment: QSAE
Date: |  |  |  | Date: |  |  | Date: | Date:

## Risk Rating
Simple Risk Assessment Methodology
1 | Rate the potential consequences of the hazard occuring using the following table
| Consequences | Description
| Insignificant | No injuries, low financial loss (eg. < 1% contract value)
| Minor | First aid treatment, medium financial loss (eg. 5% contradt value
| Moderate | Medical treatment required, high financial loss (eg. 10% contract value
| Major | Extensive injuries, loss of productivive time, major financial loss (eg 20% contract value
| Catastrophic | Death, huge financial loss (eg. > 20% contract value)
2 | Estimate the likelihood of the hazard causing a problem, using the following table
| Likelihood | Description
| Rare | The event may only occur in an exeptional circumstance
| Unlikely | The event could occur at some time during the contract
| Likely | The event is quite likely to occur at some time during the contract
| Very likely | The event will probably occur during the contract
| Almost certain | The event is expected to occur during the contract
3 | Determine the risk level using the following matrix
| Consequence | Likelihood
|  | Almost Certain | Very likely | Likely | Unlikely | Rare
| Insignificant | significant | moderate | low | low | low
| Minor | significant | significant | moderate | low | low
| Moderate | high | significant | significant | moderate | moderate
| Major | high | high | significant | significant | significant
| Catastrophic | high | high | high | high | significant
4 | Rating Definition
| High | Unacceptable risk level. Immediate actions required to eliminate or reduce
this risk level.
| Significant | Serius monitor requried, prepare for contigency plan
| Moderate | Appropriate controls are required.
| Low | Controls may still be justified.