## Sheet1
MCC TECHNIQUE ISO 45001 CERTIFICATION
No | Activities | April |  |  |  | May |  |  |  | Jun |  |  |  | July
|  | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4
1 | ISO 45001 Awareness Training | bar: April Wk3
2 | Documentation | bar: April Wk3 to May Wk1
3 | Implementation | bar: April Wk1 to Jun Wk2
4 | Internal audit training | May Wk1: 2025-05-06
5 | Internal audit | May Wk3: 21-22 May
6 | Management review | May Wk4: 2025-05-28
7 | Certification audit | Jun Wk1: Stg 1 - 3 Jun; Jun Wk2: Stg 2 - 12 & 13 Jun