## Inspection and Test Plan - Mech
HEXATECH |  | PROJECT DEPARTMENT |  |  |  | Issue No.: 1 | Document Effective Date: 01 Mar 2017 |  | Page 1 of 2
|  | Inspection and Test Plan - Mechanical Works |  |  |  | Revision No.: 0 |  |  | Document Ref: PD-REC-ITP-MW
Project Name |  |  |  |  | Customer Name
Project Reference |  |  |  |  | Consultant Name
No. | Inspection / Test Activity |  | Point of Inspection / Test | Responsibility | Acceptance Criteria & Frequency | Verifying Document |  | Action By:
[8 empty] | Own | Consultant | Customer
2.0 | MECHANICAL WORKS
2.1 | Receiving Inspection of Electrical |  | - Upon delivery to site | PE, DE, PC, SS | - Physical condition | - Receiving Inspection |  | I, N
| materials & equipment. |  | - Upon delivery to store | Storekeeper | - Correct type / rating | Checklist
| - Refer Project Materials List |  | (before delivery conduct factory |  | - Frequency of receiving | - D.O & P.O
|  |  | witness test if required by customer, |  | inspection shall as stated | - Project Drawing
|  |  | project manager or consultant) |  | in Project Material List
2.2 | In-Process Inspection & Testing |  | - During partial / full completion of | PM/CM | - Refer to Checklist and | - Work Procedure |  | I
| - Piping support installation |  | installation works prior handover | PC, PE, DE | project specification | - Project Drawing
| - Pipes, Fitting & Valves installation |  | to customer. |  | - For every partial/full | - Installation checklist
| - Ducting installation |  |  |  | completion of installation
| - Chiller, AHU, Aircond Installation |  |  |  | works as applicable.
- to be expanded as required
2.3 | Final Inspection & Testing of |  | Upon partial / full completion of | PM/CM | - Refer to Checklist and | - Work Procedure |  | I,N,A,F | J, CC
| Mechanical Works |  | installation works prior handover | PC, PE, DE | project specification | - Project Drawing
| - Incl. of all items in 2.2 above |  | to customer |  |  | - Installation checklist
- Chiller
- Air Handling Units
Note: I - Implement ; J - Joint Inspection ; N - Notify ; A - Obtain Approval ; F- File ; CC - Copy
HEXATECH |  | PROJECT DEPARTMENT |  |  |  | Issue No.: 1 | Document Effective Date: 01 Mar 2017 |  | Page 2 of 2
|  | Inspection and Test Plan - Mechanical Works |  |  |  | Revision No.: 0 |  |  | Document Ref: PD-REC-ITP-MW
Project Name |  |  |  |  | Customer Name
Project Reference |  |  |  |  | Consultant Name
No. | Inspection / Test Activity |  | Point of Inspection / Test | Responsibility | Acceptance Criteria & Frequency | Verifying Document |  | Action By:
[8 empty] | Own | Consultant | Customer
| - Air Conditioning Units |  |  |  | - For every partial / full | - Test Procedure
| - Piping & Ducting |  |  |  | completion of installation | - Test Report
| - To be expanded as required |  |  |  | works as applicable.
2.4 | Final Inspection & Handover of |  | Upon partial / full handover of | PM/CM | Refer to Defects & | Defects & Outstanding Works |  | I, N, A, F | J, CC | CC
| Project to customer |  | project to customer. | PC, PE, DE | Outstanding Works Summary | Summary List or customer
| - Incl. of all items in 1.3 above |  |  |  | List or customer provided | provided document / checklist
[5 empty] | documents / checklist. | - Test Report
[5 empty] | For every partial / full | - Project Drawing
[5 empty] | handover of project. | - Project Specifiation
2.5 | Inspection & Test by Authorities |  | Upon partial / full completion of | PM/CM | Refer to Project Specs. & | Approval / Supporting Letter |  | I, N, A, F | J, CC | CC
| ( JBA, TNB, TMB, Bomba, JKR, |  | installation works prior handover | PC, PE, DE | requirements of authorities | from Authhorities
| IWK, JPS, etc as applicable) |  | to customer
Note: I - Implement ; J - Joint Inspection ; N - Notify ; A - Obtain Approval ; F- File ; CC - Copy
Prepared by: |  |  |  | Approved by: |  |  | Recorded by:
Signature: |  |  |  | Signature: |  |  | Signature:
Name: |  |  |  | Name: |  |  | Name:
Appointment: |  |  |  | Appointment: |  |  | Appointment:
Date: |  |  |  | Date: |  |  | Date: