## May2022
HEXATECH |  | PROJECT DEPARTMENT |  |  | Issue No.: 1 | Document Effective Date: 01 Mar 2017 | Page 1 of 5
|  | Monthly Site Progress Report |  |  | Revision No.: 0 |  | Document Ref.: PD-REC-MSPR
Project Title: |  |  | Proposed Replacement Of MV Switchgear, Transformer & LV Main Switchboard For Menara TA One, Kuala Lumpur.
Progress Report No.: |  |  | 01/2022
Progress Report Date: |  |  | 09 May 2022
Overall Work Program: |  |  | Work Program as of 09 May 2022 as per attached.
Other Attachment: |  |  | Shut Down Timeline as of 09 May 2022 as per attached.
Item | Location |  |  | Material Status | % Completion | Date | Remarks
1 | Tamco Switchgear for 21st Floor |  |  |  | 90% | 2022-04-27
2 | LV MSB & EMSB 1 for Ground Floor |  |  |  | 90% | 2022-04-26
Hexatech SDN. BHD. |  | PROJECT DEPARTMENT |  |  | Issue No.: 1 | Document Effective Date: 01 Aug 2017 | Page 2 of 5
|  | Monthly Site Progress Report |  |  | Revision No.: 0 |  | Document Ref.: PD-REC-MSPR
Progress Report No.: 01/2022 |  |  |  | Date: 9 May 2022
Item | Location |  |  | Material Status | % Completion | Date | Remarks
2 | LV MSB & EMSB 1 for Ground Floor
3 | HT DC Battery Charger (2 units) |  |  |  | 100% | 2022-04-26
Hexatech SDN. BHD. |  | PROJECT DEPARTMENT |  |  | Issue No.: 1 | Document Effective Date: 01 Aug 2017 | Page 3 of 5
|  | Monthly Site Progress Report |  |  | Revision No.: 0 |  | Document Ref.: PD-REC-MSPR
Progress Report No.: 01/2022 |  |  |  | Date: 9 May 2022
Item | Location |  |  | Material Status | % Completion | Date | Remarks
4 | Remote Control Panel (2 units) |  |  |  | 100% | 2022-04-28
5 | Cat6 cabling at Ground Floor, 21st Floor & 22nd Floor |  |  |  | 100% | 19/4/2022 to 30/4/2022
Hexatech SDN. BHD. |  | PROJECT DEPARTMENT |  |  | Issue No.: 1 | Document Effective Date: 01 Aug 2017 | Page 4 of 5
|  | Monthly Site Progress Report |  |  | Revision No.: 0 |  | Document Ref.: PD-REC-MSPR
Progress Report No.: 01/2022 |  |  |  | Date: 9 May 2022
Item | Location |  |  | Material Status | % Completion | Date | Remarks
5 | Cat6 cabling at Ground Floor, 21st Floor & 22nd Floor
Hexatech SDN. BHD. |  | PROJECT DEPARTMENT |  |  | Issue No.: 1 | Document Effective Date: 01 Aug 2017 | Page 5 of 5
|  | Monthly Site Progress Report |  |  | Revision No.: 0 |  | Document Ref.: PD-REC-MSPR
Progress Report No.: 01/2022 |  |  |  | Date: 9 May 2022
Project Progress Status
6 | Project Duration / Extension of Time (EOT)
| Project Duration |  |  | Document Reference | Date | Remarks
| 18 Mar 2022 to 15 Jul 2022 |  |  | Letter Of Intention - ABCSB/MTA/MCCT/02 | 18 Mar 2022 | Letter of Award will be issued.
No EOT
7 | Variation Order
| Variation | Date |  | Description / Engineer Instruction | Quotation & Date | Amount (RM) | Approval
| 1 | 05 May 2022 |  | Supply & Install Temporary Essential Supply During Shut Down / KVA/MTA/MCCT/EI/01 dated 26 Apr 2022 | PR602-TAPSB-MTAO-ELEC-3330 dated 05 May 2022 | 90000 | Not Yet
8 | Progress Claims / Retention
| Claim No. | Date |  | Claim Details / Evaluation Period / Retention | Engineer Approval Date | Amount (RM) | Payment Issue Date
None
9 | Contact Directory
| PIC | Appointment / Name / Hp No.
| ABC Sdn Bhd | Facility Manager - Mr xxxx - 012-906 xxxx
| ABC Sdn Bhd | Chargeman - En xxxx - 019-708 xxxx
| ABC Consulting | Consultant - Ir xxxx - 016-478 xxxx
| Hexatech | Project Director - Mr xxxx - 012-6622 xxxx
| Hexatech | Project Manager - Mr xxxx - 016-6622 xxx
| Hexatech | Project Engineer - Mr. xxxx - 012-999 xxxx
| Hexatech | Project Executive - En. xxxx- 016 6622 xxxx
| Hexatech | Contracts Manager - Ms xxxx - 019-655 xxxx
10
11 | Issue Of Concern / To Follow Up
| No. | Action Item |  |  |  | Action By | Status
| 1 | Letter of Award (targeted 1st week of May 2022 to issue). |  |  |  | ABC Sdn Bhd | Not Yet
| 2 | Supply of Diesel - max capped at 3,500 litres @ RM3.90/litre. New rate: RM4.60/litre. |  |  |  | Hexatech | Highlighted
| 3 | Tenant request for genset support. |  |  |  | Hexatech | Highlighted
| 4 | Liaison with TNB for CT witness and shut down (for 2nd shut down). |  |  |  | Hexatech | Highlighted
| 5 | Work permit application - for 1st & 2nd shut down. |  |  |  | Hexatech | Highlighted
Prepared by: |  |  |  | Verified by: | Recorded by:
Signature: |  |  |  | Signature: | Signature:
Name: |  |  |  | Name: | Name:
Appointment: Project Executive |  |  |  | Appointment: Project Manager | Appointment: | Document Controller
Date: …. May 2022 |  |  |  | Date: xxx May 2022 | Date: | xxx May 2022
SAMPLE REPORT

## Work Program
HEXATECH |  |  | PROJECT DEPARTMENT | [30 empty] | Issue No.: 1 | [5 empty] | Document Effective Date: 01 Aug 2017 | [8 empty] | Page 1 of 1
|  |  | Work Program - Menara TA One | [30 empty] | Revision No.: 0 | [14 empty] | Document Ref: PD-REC-WP
PROJECT NAME : Proposed Replacement Of MV Switchgear, Transformer & LV Main Switchboard For Menara TA One, Kuala Lumpur. | [35 empty] | PROJECT MANAGER: XXXX XXXX | [12 empty] | DATE: 09 May 2022 (Revision 2)
NO. | ACTIVITY | DAY | START DATE | END DATE | MARCH 2022 | [13 empty] | APRIL 2022 | [29 empty] | MAY 2022 | [30 empty] | JUN 2022
[5 empty] | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[5 empty] | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | F
[61 empty] | SHUT DOWN | [20 empty] | SHUT DOWN | [6 empty] | AMFB OFF
1 | Letter of Intention / Letter Of Award | 2 | 2022-03-18 | 2022-05-11 | bar: MARCH 2022 18 F; MAY 2022 11 W
2 | Mobilization - Preliminaries & Site Measurements | 29 | 2022-03-18 | 2022-04-15 | bar: MARCH 2022 18 F to APRIL 2022 15 F
3 | Application To TNB for CT Calibration & Power Shut Down (By Consultant) | 19 | 2022-03-21 | 2022-04-08 | bar: MARCH 2022 21 M to APRIL 2022 19 T
4 | GF & L21 Thermographic Scanning & Earthing System Test | 2 | 2022-04-04 | 2022-04-05 | bar: APRIL 2022 4 M to APRIL 2022 5 T
5 | Prepare & Submit GF & L21 MV Switchgear Shop Drawings & Approval | 26 | 2022-03-25 | 2022-04-19 | bar: MARCH 2022 25 F to APRIL 2022 19 T
6.1 | L21 New MV Switchgear (3 Panels) + DC Battery + RCP - Fabrication & FAT | 35 | 2022-04-04 | 2022-05-10 | MAY 2022 10 T: FAT
6.2 | L21 Old MV Switchgear (3 Panels) + Old DC Battery - Dismantle & Disposal | 3 | 2022-05-13 | 2022-05-15 | bar: MAY 2022 13 F to MAY 2022 15 SU
6.3 | L21 New MV Switchgear (3 Panels) + DC Battery + RCP - Delivery To Site & Installation | 6 | 2022-05-11 | 2022-05-16 | MAY 2022 12 TH: Del
6.4 | L21 New MV Switchgear (3 Panels) - Relay Calibration, Hipot Test, T&C | 2 | 2022-05-15 | 2022-05-16 | MAY 2022 16 M: T&C
7.1 | L21 MV Cable for T3 & T4 - Dismantle, Replace New Cable, Megger Test & MV Joints | 3 | 2022-05-13 | 2022-05-15 | bar: MAY 2022 13 F to MAY 2022 15 SU
7.2 | L21 New Control Cable from T3 & T4 to New MV Switchgear | 2 | 2022-05-14 | 2022-05-15 | bar: MAY 2022 14 S to MAY 2022 15 SU
8.1 | L21 (T3 & T4) Transformer Relocate Temperature Indicator | 2 | 2022-05-14 | 2022-05-15 | bar: MAY 2022 14 S to MAY 2022 15 SU
8.2 | L21 (T3 & T4) Transformer Servicing & T&C | 2 | 2022-05-14 | 2022-05-15 | MAY 2022 15 SU: T&C
9 | Prepare & Submit GF & L21 LV MSB/EMSB Shop Drawings & Approval | 29 | 2022-03-22 | 2022-04-19 | bar: MARCH 2022 22 T to APRIL 2022 19 T
10.1 | GF LV MSB/EMSB (9 Tiers) - Fabrication & FAT | 37 | 2022-04-04 | 2022-05-10 | MAY 2022 11 W: FAT
10.2 | GF LV MSB/EMSB (9 Tiers) - Dismantle & Disposal | 3 | 2022-05-13 | 2022-05-15 | bar: MAY 2022 13 F to MAY 2022 15 SU
10.3 | GF LV MSB/EMSB (9 Tiers) - Delivery To Site, Installation, Relay Calibration & T&C | 5 | 2022-05-12 | 2022-05-16 | MAY 2022 12 TH: Del; MAY 2022 16 M: T&C
11.1 | GF New MV Switchgear (4 Panels) + DC Battery + RCP - Fabrication & FAT | 54 | 2022-04-04 | 2022-05-27 | MAY 2022 27 F: FAT
11.2 | GF Old MV Switchgear (4 Panels) + Old DC Battery - Dismantle & Disposal | 3 | 2022-06-03 | 2022-06-05 | bar: JUN 2022 3 F to JUN 2022 5 SU
11.3 | GF New MV Switchgear (4 Panels) + DC Battery + RCP - Delivery To Site & Installation | 5 | 2022-05-31 | 2022-06-06 | MAY 2022 31 T: Del
11.4 | GF New MV Switchgear (4 Panels) - Relay Calibration, Hipot Test, T&C | 2 | 2022-06-05 | 2022-06-06 | JUN 2022 6 M: T&C
12 | GF New MV Switchgear - Dismantle, Replace & install new TNB Meter Kiosk & CT Calibration with TNB Witness on site | 2 | 2022-06-04 | 2022-06-05 | bar: JUN 2022 4 S to JUN 2022 5 SU
13.1 | GF MV Cable for T1 & T2 - Dismantle, Replace New Cable, Megger Test & MV Joints | 3 | 2022-06-03 | 2022-06-05 | bar: JUN 2022 3 F to JUN 2022 5 SU
13.2 | GF New Control Cable from T1 & T2 to New MV Switchgear | 3 | 2022-06-04 | 2022-06-05 | bar: JUN 2022 4 S to JUN 2022 5 SU
14.1 | GF (T1 & T2) Transformer Relocate Temperature Indicator | 2 | 2022-06-04 | 2022-06-05 | bar: JUN 2022 4 S to JUN 2022 5 SU
14.2 | GF (T1 & T2) Transformer Servicing & T&C | 2 | 2022-06-04 | 2022-06-05 | JUN 2022 5 SU: T&C
15.1 | L21 New LV MSB/EMSB (11 Tiers) - Fabrication & FAT | 46 | 2022-04-11 | 2022-05-26 | MAY 2022 26 TH: FAT
15.2 | L21 Old LV MSB/EMSB (11 Tiers) - Dismantle & Disposal | 3 | 2022-06-03 | 2022-06-05 | bar: JUN 2022 3 F to JUN 2022 5 SU
15.3 | L21 New LV MSB/EMSB (11 Tiers) - Delivery To Site, Installation, Relay Calibration & T&C | 6 | 2022-05-30 | 2022-06-06 | MAY 2022 30 M: Del; JUN 2022 6 M: T&C
15.4 | L21 LV MSB/EMSB Incoming & Outgoing MICC Cables Disconnection & Re-connections | 3 | 2022-06-03 | 2022-06-05 | bar: JUN 2022 3 F to JUN 2022 5 SU
16 | Prepare & Submit GF 750kVA Genset AMF Board Shop Drawings & Approval | 9 | 2022-04-11 | 2022-04-19 | bar: APRIL 2022 11 M to APRIL 2022 19 T
16.1 | GF New 750kVA Genset AMF Board (3 Tiers) - Fabrication & FAT | 32 | 2022-04-25 | 2022-05-26 | MAY 2022 26 TH: FAT
16.2 | GF Old 750kVA Genset AMF Board (3 Tiers) - Dismantle & Disposal | 2 | 2022-06-11 | 2022-06-12 | bar: JUN 2022 11 S to JUN 2022 12 SU
16.3 | GF New 750kVA Genset AMF Board (3 Tiers) - Delivery To Site, Installation & T&C | 3 | 2022-05-30 | 2022-06-12 | MAY 2022 30 M: Del; JUN 2022 12 SU: T&C
16.4 | GF 750kVA Genset AMF Board Outgoing MICC Cables Disconnection & Re-connections | 2 | 2022-06-11 | 2022-06-12 | bar: JUN 2022 11 S to JUN 2022 12 SU
17 | GF 2000kVA Genset AMF Board - Check, Replace & Install new 2500A TPN ACB & T&C | 2 | 2022-06-11 | 2022-06-12 | JUN 2022 12 SU: T&C
18 | GF & L21 New LV MSB/EMSB Install Cat 6 cabling & link DPM reading to current BMS system. | 5 | 18-Apr | 30-Apr 16-May 6-Jun | bar: APRIL 2022 18 M to APRIL 2022 19 T; APRIL 2022 30 S; MAY 2022 16 M; JUN 2022 6 M
19.1 | GF & L21 Plant Room - Framed SLD, Rubber Mats, Danger Sign, First Aid Kit, Maint. Kits | 1 | 2022-06-13 | 2022-06-30 | [91 empty] | 30/6 | bar: JUN 2022 13 M to JUN 2022 16 F
19.2 | GF & L21 Plant Room - As Build Drawings, O&M Manual, System Training | 1 | 2022-06-13 | 2022-06-30 | [91 empty] | 30/6 | bar: JUN 2022 13 M to JUN 2022 16 F
20 | Handing Over / Taking Over / Certificate of Completion Issuance | 1 | 2022-06-13 | 2022-06-30 | [91 empty] | 30/6 | bar: JUN 2022 13 M to JUN 2022 16 F
Scheduled Days of Completion (18-Mar-2022 to 30-Jun-2022) |  |  | 105 | Days | MARCH 2022 19 S: Legend:; MAY 2022 1 SU: Prepared By:; MAY 2022 16 M: Verified By:; JUN 2022 1 W: Remarks:
Actual Days of Completion |  |  | 13 | Days | MARCH 2022 20 SU: Scheduled/Planned Days; MARCH 2022 28 M: Completion Days; APRIL 2022 3 SU: Report Status Date; APRIL 2022 9 S: FAT; APRIL 2022 10 SU: Factory Acceptance Test; APRIL 2022 17 SU: Del; APRIL 2022 18 M: Delivery To Site; APRIL 2022 23 S: T&C; APRIL 2022 24 SU: Testing & Commissioning; MAY 2022 5 TH: xxxxx xxxx (Project Executive); MAY 2022 20 F: xxx xxx xxx (Project Manager)
Ahead / Behind * |  |  | 0 | Days | MAY 2022 5 TH: Date: 09-May-2022; MAY 2022 20 F: Date: 09-May-2022

## Updated 9.5.2022
MENARAT TA ONE KL - ELECTRICAL SERVICES - SHUT DOWN TIMELINE
[5 empty] | Groundfloor |  |  |  |  | 21st Floor
Date | Time |  | 21st Floor | Ground Floor | VCB | Genset | MSB 1 | MSB 2 | EMSB 1 | VCB | MSB 3 | MSB 4 | EMSB 2
2022-05-14 | 1.00 am | EMSB 1 (GF) Change over to Genset Supply |  | Run Genset - to Power up EMSB 1 | ON | ON | ON | ON | ON | ON | ON | ON | ON
|  | EMSB 2 (21st) Change over to Genset Supply | Run Genset - to Power up EMSB 2
| 1.30 am | Shutdown MSB 3 & 4 |  |  | ON | ON | ON | ON | ON | ON | OFF | OFF | ON
| 1.30 am | Shutdown VCB & Tx at 21st |  |  | ON | ON | ON | ON | ON | OFF | OFF | OFF | ON
| 2.00 am | Shutdown MSB 1 & 2 |  |  | ON | ON | OFF | OFF | ON | OFF | OFF | OFF | ON
| 2.00 am | Shutdown VCB feeder from GF |  |  | ON | ON | OFF | OFF | ON | OFF | OFF | OFF | ON
|  |  | Start Replacing VCB at 21st Floor | Remove all LV cables from MSB 1 & 2 | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | ON
|  |  | Change New HT Cable from switchgear to TX | Replace LV MSB 1 & 2 | OFF | ON | OFF | OFF | ON
|  |  | HT Cable Termination |  | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | ON
|  |  | Servicing Tx |  | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | ON
|  |  | Remote Control Panel for Switchgear 21st Floor |  | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | ON
|  |  | Relocation of Temp controller |  | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | ON
|  |  | HT System T & C |  | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | ON
| 9.00 pm | Power VCB & Tx at 21st FLR | Changeover to TNB Supply |  | ON | ON | OFF | OFF | ON | ON | OFF | OFF | ON
2022-05-14 | 9.00 pm | Power Up MSB 3 & 4 , EMSB 2 | Activity Complete |  | ON | ON | OFF | OFF | ON | ON | ON | ON | ON
[5 empty] | ON | ON | OFF | OFF | ON | ON | ON | ON | ON
2022-05-16 | 9.00 am | Power up MSB 1 & 2 |  | Power Up MSB 1 & 2 | ON | ON | OFF | OFF | ON | ON | ON | ON | ON
| 10.00am | Divert EMSB 1 to temporary supply (MSB 1&2 to EMSB) |  | 1) To Connect temporary cable from MSB to EMSB GF to LV21 (Tenant UPS) | ON | OFF | ON | ON | OFF | ON | ON | ON | ON
|  |  |  | 2) To Connect temporary cable from MSB to EMSB GF to LV21 (Landlord CA Supply) | ON | OFF | ON | ON | OFF | ON | ON | ON | ON
|  |  |  | 3) To connect temporary cable from MSB to EMSB GF HT & LV RM DBs | ON | OFF | ON | ON | OFF | ON | ON | ON | ON
| 11.00am | Shut down EMSB 1 (GF) |  | Replace EMSB 1 | ON | OFF | ON | ON | OFF | ON | ON | ON | ON
| 12.00pm-5pm |  |  |  | ON | OFF | ON | ON | Partial Supply | ON | ON | ON | ON
| 5.00 pm | Divert EMSB 1 to temporary supply to permenant supply |  | 1) To Connect temporary cable from MSB to EMSB GF to LV21 (Tenant UPS) | ON | OFF | ON | ON | OFF | ON | ON | ON | ON
|  |  |  | 2) To Connect temporary cable from MSB to EMSB GF to LV21 (Landlord CA Supply) | ON | OFF | ON | ON | OFF | ON | ON | ON | ON
|  |  |  | 3) To connect temporary cable from MSB to EMSB GF HT & LV RM DBs | ON | OFF | ON | ON | OFF | ON | ON | ON | ON
| 6.00 pm | Power up EMSB 1 |  | Power up EMSB 1 | ON | ON | ON | ON | ON | ON | ON | ON | ON
|  | Shutdown Genset |  | Activity Complete | ON | OFF | ON | ON | ON | ON | ON | ON | ON
|  |  | 21st Floor | Ground Floor | Groundfloor |  |  |  |  | 21st Floor
[5 empty] | VCB | Genset | MSB 1 | MSB 2 | EMSB 1 | VCB | MSB 3 | MSB 4 | EMSB 2
2022-06-04 | 1.00 am | EMSB 1 (GF) Change over to Genset Supply |  | Run Genset - to Power up EMSB 1 | ON | ON | ON | ON | ON | ON | ON | ON | OFF
|  | Temporay Power Supply for L21 Switchroom room from UPS Riser | 1)To Connect Tempory Cable to L21 Switchroom DB from UPS |  | ON | ON | ON | ON | ON | ON | OFF | OFF | OFF
|  | Divert EMSB Incoming MICC Cables to Junction Box and prepare Temporary 400A Panel | 2)Divert EMSB 2 Incoming MICC Cables to Junction Box and prepare Temporary 400A Panel |  | ON | ON | ON | ON | ON | OFF | OFF | OFF | OFF
|  |  | 3)Dirvert EMSB 2 outgoing cable for EMSB LV 21 to LV 35 (Tenant UPS) |  | ON | ON | ON | ON | ON | OFF | OFF | OFF | OFF
|  |  | 4)Dirvert EMSB 2 outgoing cable for EMSB LV 21 to LV 35 (Landlord CA Supply) |  | ON | ON | ON | ON | ON | OFF | OFF | OFF | OFF
|  |  | 5)Dirvert EMSB 2 outgoing cable for EMSB SB - HZL (High Level Lift) |  | ON | ON | ON | ON | ON | OFF | OFF | OFF | OFF
| 3.00 am |  | 6)Dirvert EMSB 2 outgoing cable for EMSB SB - LZL (Low Level Lift) |  | ON | ON | ON | ON | ON | OFF | OFF | OFF | OFF
| 4.00 am |  |  |  | ON | ON | ON | ON | ON | OFF | OFF | OFF | Partial Supply
| 1.00 am | Shutdown MSB 3 & 4 |  |  | ON | ON | ON | ON | ON | OFF | OFF | OFF | OFF
| 1.30 am | Shutdown VCB & Tx at 21st | Remove all LV cables from MSB 3 & 4, EMSB 2 |  | ON | ON | ON | ON | ON | OFF | OFF | OFF | OFF
| 2.00 am | Shutdown 21st VCB feeder from GF |  |  | ON | ON | ON | ON | ON | OFF | OFF | OFF | OFF
| 2.00am | TNB Shutdown incoming |  |  | OFF | ON | OFF | OFF | ON
|  |  |  | Start Replacing VCB at GF Floor | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | OFF
Change New HT Cable from switchgear to TX
|  |  |  | HT Cable Termination | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | OFF
|  |  |  | Servicing Tx | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | OFF
|  |  |  | Replacement of Metering Kiosk | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | OFF
|  |  |  | Relocation of Temp controller | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | OFF
|  |  |  | Remote Control Panel for Switchgear 21st Floor | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | OFF
|  |  |  | HT System T & C | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | OFF
2022-06-04 | 9.00pm | TNB install Metering Meter |  |  | OFF | ON | OFF | OFF | ON | OFF | OFF | OFF | Partial Supply
| 10.00pm | TNB Power on incoming VCB Feeder |  |  | ON | ON | OFF | OFF | ON | OFF | OFF | OFF | Partial Supply
|  | Power VCB & Tx at 1st FLR |  |  | ON | ON | OFF | OFF | ON | OFF | OFF | OFF | Partial Supply
|  | Power Up MSB 1 & 2 & EMSB 1 |  | Activity Complete | ON | ON | ON | ON | OFF | OFF | OFF | OFF | Partial Supply
2022-06-06 | 3.00 pm | Off Temporary DB at 21ft | 1)To Dismental incoming cable for Temporary DB |  | ON | OFF | ON | ON | OFF | OFF | OFF | OFF | OFF
|  | Shutdown Genset | 2)Dirvert EMSB 2 outgoing cable for EMSB LV 21 to LV 35 (Tenant UPS) from Temporary DB |  | ON | OFF | ON | ON | OFF | OFF | OFF | OFF | OFF
|  |  | 3)Dirvert EMSB 2 outgoing cable for EMSB LV 21 to LV 35 (Landlord CA Supply) from Temporary DB |  | ON | OFF | ON | ON | OFF | OFF | OFF | OFF | OFF
|  |  | 4)Dirvert EMSB 2 outgoing cable for EMSB SB - HZL (High Level Lift) from Temporary DB |  | ON | OFF | ON | ON | OFF | OFF | OFF | OFF | OFF
| 5.00pm |  | 5)Dirvert EMSB 2 outgoing cable for EMSB SB - LZL (Low Level Lift) from Temporary DB |  | ON | OFF | ON | ON | OFF | OFF | OFF | OFF | OFF
| 6.00pm | Power On 21ft VCB from GF |  |  | ON | OFF | ON | ON | OFF | ON | OFF | OFF | OFF
|  | Power VCB & Tx at 21st FLR |  |  | ON | OFF | ON | ON | OFF | ON | ON | ON | ON
|  | Power Up MSB 3 & 4 & EMSB 2 |  |  | ON | OFF | ON | ON | OFF | ON | ON | ON | ON
|  |  | Activity Complete |  | ON | OFF | ON | ON | OFF | ON | ON | ON | ON
Updated: 9 May 2022