## Sheet1
| Company Name | HEXATECH |  |  |  |  | Project Budgetary Costing Form
| Category | Project |  |  |  |  | Issue No. 1
| ISO File No. | HX/PRM/H/603/P0002 |  |  |  |  | Revision No. 0
| Project Name | INFINEON KULIM - ELECTRICAL SERVICES |  |  |  |  | Document Effective Date: 01 Mar 2017
| Costing No | 17/P 0002 |  |  |  |  | Document Ref.: PD-REC-PBCF
| Requestor | Abdul Samad
| Commencement Date | 2017-06-01
| Estimated Completion Date | 2017-06-10
| Submission date | 2017-06-01 17:06
Item | Description | Sales Sum | Budget Sum | Profit |  | Actual | Exp Awarded | Variance | MRF No. | MOA No.
|  |  |  | Amount | % | Awarded
1 | ELECTRICAL SERVICES :- | 1037768 | 774187 | 263581 | 25.4 | 19304.07 | 754882.93 | 0 | - | -
1.1 | Preliminaries (1 lot) | 27490 | 20600 | 6890 | 25.06 | 17004.07 | 3595.93 | 0 | 0002, 0003, | 0002
1.2 | Switchboards (1 lot) | 398500 | 280980 | 117520 | 29.49 | 0 | 280980 | 0 | - | -
1.3 | External Submain Cabling (1 lot) | 175989 | 84388 | 91601 | 52.05 | 2300 | 82088 | 0 | 0016, 0050 | 0016
1.4 | Internal Submain Cabling (1 lot) | 91844 | 0 | 91844 | 100 | 0 | 0 | 0 | - | -
1.5 | Final Sub-Circuit (1 lot) | 199045 | 11100 | 187945 | 94.42 | 0 | 11100 | 0 | - | -
1.6 | Infra-Structure Works (1 lot) | 144900 | 43510 | 101390 | 69.97 | 0 | 43510 | 0 | - | -
1.7 | Labour only (1 lot) | 0 | 333609 | -333609 | 0 | 0 | 333609 | 0 | - | -
Total Contract Sum |  |  | 1037768 | 774187 |  | 25.4 | 19304.07 | 754882.93
Less C/S & PC Sum |  |  | 0 | 0
Actual Total Contract Sum |  |  | 1037768 | 774187
|  | Actual Profit | 263581 |  |  | Projected Profit |  | 263581
|  | Profit Percentage | 25.4% |  |  | Profit Percentage |  | 25.4%