## Cert
HEXATECH |  |  |  | Project Progress Claim Form
No. 18, Jalan Industri PBP 9, Taman Industri Pusat Bandar Puchong, |  |  |  | Issue No.: 1
47099 PUCHONG, Selangor Darul Ehsan, MALAYSIA. |  |  |  | Revision No.: 0
Tel. No.: +603 8068 1811 Fax No.: +603 8068 1722 |  |  |  | Document Effective Date: 01 Mar 2017
Document Ref. No.: PD-REC-PPCF
TO: |  |  |  | Progress Claim No. ………………..
Project : …………………………
| Attention: |  |  | Date : ……………………………
PROJECT :
SCOPE :
TOTAL VALUE OF WORK EXECUTED : |  |  |  |  | RM | 37365
Less : |  |  |  |  | RM
TOTAL VALUE OF VARIATION ORDER CLAIM : |  |  |  |  | RM
TOTAL VALUE OF WORK COMPLETED TO DATE IN ACCORDANCE |  |  |  |  | RM | 37365
WITH CONTRACT & VARIATION THERE TO :
[5 empty] | RM | 0
LESS : RETENTION IN ACCORDANCE WITH CONTRACT (5%) |  |  |  |  | RM | 1868.25
TOTAL AMOUNT NOW CLAIMED FOR PAYMENT TO DATE IN ACCORDANCE |  |  |  |  | RM | 35496.75
WITH CONTRACT
LESS : TOTAL AMOUNT CERTIFIED / PAID:
Progress Certification No. 1 |  | RM | 6508 | (Paid on 15 Apr 2015)
Progress Certification No. 2 |  | RM | 14657 | (Paid on 18 May 2015)
21165
[5 empty] | RM | 21165
PROGRESS AMOUNT NOW CLAIM |  |  |  |  | RM | 14331.75
|  |  | GST 6% |  | RM | 859.905
PROGRESS AMOUNT TO PAY (RM): |  |  |  |  | RM | 15191.655
CONTRACT PARTICULARS (FOR INFORMATION)
CONTRACT VALUE AS AWARDED : |  | RM | 55220 | LIMIT OF RETENTION : | RM | 2761
ADD - Variation Order (Additional Works) |  | RM | 0 | PERFORMANCE BOND : | RM | N/A
LESS - Omission or Contingency Sum |  | RM | 0 | TOTAL LESS RETENTION : | RM | 2761
TOTAL ADJUSTED CONTRACT SUM : |  | RM | 55220
WE HEREBY CLAIM THAT IN ACCORDANCE WITH THE TERM OF THE CONTRACT WITH THE ABOVE
AMOUNT OF MALAYSIA RINGGIT :
Forty Five Thousand Seven Hundred Fifty Nine and Cents Fifty Six Only.
Submitted by: |  |  |  | Receipt Acknowledgement:
Signature: |  |  |  | Signature:
Name: |  |  |  | Name: |  | Company Chop
Appointment: Project Manager |  |  |  | Appointment:
Date: |  |  |  | Date:

## Original Contract
HEXATECH
Project Name : …………………….
Progress Claim No.: …………………….
Date: ………………………..
|  |  |  | Award Amount | LAST CLAIM |  | THIS CLAIM |  | Amend
Item | Description | Qty / Unit |  |  | Work Done | Amount | Work Done | Amount | Work Done | Amount | Remarks
|  |  |  | (RM) | (%) | (RM) | (%) | (RM) | (%) | (RM)
FIRE PROTECTION SYSTEM
1 | Preliminaries
1.1 | Provision for the preparation of all shop drawings | 1 | lot | 450 | 0% | 0 | 0% | 0
1.2 | To provide 'as-built' drawings and Operation and | 1 | lot | 450 | 0% | 0 | 0% | 0
Maintenance Manuals (4 Hard Bound Copies)
1.3 | Testing And Commissioning
a | Testing and commissioning of the complete system | 1 | lot | 450 | 0% | 0 | 0% | 0
b | BOMBA testing and all fees payable including fire door, hydrant, and emergency light. | 1 | lot | 750 | 0% | 0 | 0% | 0
c | Servicing and maintenance for 12 months | 1 | lot | 2400 | 0% | 0 | 0% | 0
d | Any other matter not mentioned, please specified :-
i) ....................................................................
ii) ..................................................................
| Sub-Total RM - Summary 1.0: |  |  | 4500 |  | 0 |  | 0
2 | HOSE REEL SYSTEM
2.1 | Tanks and Pumpset
a | Hot dipped galvansed press steel hosereel water storage tank (1 no.) c/w 600 x 600mm manhole, piping works, vent pipe, external M.S and internal aluminium cat ladder, incoming water supply to hosereel water storage tank, water indicator, over flow, scour pipe and other related works as indicated in the drawing. | 1 | lot | 9800 | 50% | 4900 | 80% | 7840
b | Hose Reel Pump (1 no. DUTY Pump and 1 no. STANDBY Diesel Genset Pump) with Pump control switchboard c/w control cable, wiring in conduit/trunking, conduit accessories and other related works. | 1 | lot | 9850 | 50% | 4925 | 80% | 7880
C | Hose reel pipework from Hose Reel Pump and | 4 | nos. | 6800 | 50% | 3400 | 80% | 5440
c/w valves, hosereel drums and accessories
| Sub-Total RM - Summary 2.0: |  |  | 26450 |  | 13225 |  | 21160
3 | Fire Alarm System
3.1 | 12 zone fire alarm panel c/w mimic diagram and battery | 1 | lot | 3650 | 40% | 1460 | 70% | 2555
3.2 | Fire Alarm PVC wiring in G.I conduit for above ground or armour cable for underground to master alarm panel including breakglass, detector, manual call point, monitoring of pumpsets, tank level and hacking of concert slabs. | 1 | lot | 2700 | 40% | 1080 | 70% | 1890
3.3 | Smoke detetor ,heat detector , alarm bell and manual call point c/w wiring and GI conduit work.
| GF - Smoke Detector = 1 | 9 | nos | 3600 | 40% | 1440 | 70% | 2520
1F - Smoke Detector = 2
2F - Smoke Detector = 4
Roof - Smoke Detector = 2
| GF - Heat Detector = 5 | 27 | nos | 10800 | 30% | 3240 | 70% | 7560
1F - Heat Detector = 7
2F - Heat Detector = 15
Roof - Nil
| GF - Alarm Bell & Manual Call Point (Breakglass) = 2 | 8 | nos | 2400 | 30% | 720 | 70% | 1680
1F - Alarm Bell & Manual Call Point (Breakglass) = 2
2F - Alarm Bell & Manual Call Point (Breakglass) = 2
3F - Alarm Bell & Manual Call Point (Breakglass) = 2
Roof - Nil
| Sub-Total RM - Summary 3.0: |  |  | 23150 |  | 7940 |  | 16205
4 | Portable Fire Extinguisher
4.1 | ABC dry powder (9 kg) c/w Bomba Cert as per tender drawings. | 9 | nos. | 990 | 0% | 0 | 0% | 0
4.2 | CO2 (2.27 kg) c/w Bomba cert as per tender drawings. | 1 | no. | 130 | 0% | 0 | 0% | 0
4.3 | Any other matter not mentioned, please specified :-
i) ........................................................
ii) ........................................................
| Sub-Total RM - Summary 4.0: |  |  | 1120 |  | 0 |  | 0
SUMMARY OF PRICES
1.0 | Preliminaries | 1 | L/S | 4500 |  | 0 |  | 0
2.0 | HOSE REEL SYSTEM | 1 | L/S | 26450 |  | 13225 |  | 21160
3.0 | Fire Alarm System | 1 | L/S | 23150 |  | 7940 |  | 16205
4.0 | Portable Fire Extinguisher | 1 | L/S | 1120 |  | 0 |  | 0
Excludes:
a | Power incoming supply to all fire protection system equipment.
b | RC plints for storage tank and pumps.
| Grand Total (RM) |  |  | 55220 | 0 | 21165 |  | 37365 |  | 0
VARIATIONS ORDER
1) | Add Contigency Sum (if any) | RM |  | 0
2) | Add Additional Works (VO 1) | RM |  | 0
3) | Less Ommission (VO 2) | RM |  | 0
Total Variation Order (RM) |  | RM |  | 0
Prepared by: |  | Evaluation carried out by: |  |  |  |  | Verified above by:
Name: |  | Name: |  |  |  |  | Name:
Appointment: Project Manager |  | Appointment: (consultant) |  |  |  |  | Appointment: (customer representative)
Company Name: HEXATECH |  | Company Name: |  |  |  |  | Company Name:
Date: |  | Date: |  |  |  |  | Date: