## REC
HEXATECH |  |  | PROJECT MANAGEMENT | [28 empty] | Issue No.: 1 | [5 empty] | Document Effective Date: 01 Mar 2017 | [7 empty] | Page 1 of 1
|  |  | Project Schedule Tracking Table | [28 empty] | Revision No:. 0 | [13 empty] | Document Ref: PD-REC-PSTT
PROJECT NAME : …………………………………………….………………………………………….. | [17 empty] | PROJECT MANAGER: ………………………….. | [15 empty] | DATE: …………………
NO. | ACTIVITY | DAYS | START DATE | END DATE | JUNE …… | [5 empty] | JULY ….. | [29 empty] | AUG ….
[5 empty] | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Mobilization | 3 | 2010-06-25 | 2010-06-27 | bar: JUNE …… 25 to JUNE …… 27
Electrical
2 | Lighting Point | 14 | 28-Jun | bar: JUNE …… 28 to JULY ….. 11
3 | Power Point | 14 | 28-Jun | bar: JUNE …… 28 to JULY ….. 11
4 | Trunking Installation | 10 | 28-Jun | bar: JUNE …… 28 to JULY ….. 7
5 | Sub-main Cable | 10 | 9-Jul | bar: JULY ….. 9 to JULY ….. 18
6 | DB Installation | 6 | 21-Jul | bar: JULY ….. 21 to JULY ….. 26
7 | Fitting Installation | 14 | 28-Jul | bar: JULY ….. 28 to AUG …. 11
Telephone
8 | External Work | 14 | 11-Jul | bar: JULY ….. 11 to JULY ….. 24
9 | Internal Work | 14 | 29-Jun | bar: JUNE …… 29 to JULY ….. 12
Local Area Network
10 | LAN Point | 14 | 12-Jul | bar: JULY ….. 12 to JULY ….. 25
11 | Equipment Installation | 7 | 27-Jul | bar: JULY ….. 27 to AUG …. 3
PA System
12 | PA Point | 14 | 8-Jul | bar: JULY ….. 8 to JULY ….. 21
13 | Equipment Installation | 7 | 25-Jul | bar: JULY ….. 26 to AUG …. 2
14 | Street Lighting | 14 | 11-Jul | bar: JULY ….. 11 to JULY ….. 24
15 | T&C | 14 | 11-Aug | bar: AUG …. 11 to AUG …. 13
16 | Hand Over | 1 | 28-Aug
Scheduled Days of Completion |  |  | 64 | Days | AUG …. 1: Remarks:
Actual Days of Completion |  |  | 10 | Days | JULY ….. 6: Legend:; JULY ….. 9: Scheduled/Planned Days; JULY ….. 20: Actual
Ahead / Behind * |  |  | 0 | Days
PREPARED BY : |  |  |  |  | JUNE …… 25: VERIFIED BY :; JULY ….. 11: APPROVED BY :; JULY ….. 26: RECORDED BY :
| …………………………………. |  |  |  | JUNE …… 26: ………………………………….; JULY ….. 12: ………………………………….; JULY ….. 27: ………………………………….
| PROJECT EXECUTIVE |  | DATE: |  | JUNE …… 26: PROJECT MANAGER; JULY ….. 4: DATE:; JULY ….. 12: MANAGING DIRECTOR; JULY ….. 20: DATE:; JULY ….. 27: ADMIN. EXECUTIVE; AUG …. 5: DATE: